## Dashboard
VODAFONE–VOIS INTELLIGENT AI ASSISTANT
Executive Project Dashboard · Enterprise GenAI · RAG · MCP on Microsoft Azure AI Foundry
Status as at 15 Jan 2027 · Week 13 of 20 · PM: Ananya Rao · Sponsor: Rajesh Menon
OVERALL PROGRESS |  | SCHEDULE PERFORMANCE (SPI) |  |  |  | COST PERFORMANCE (CPI) |  |  |  | BUDGET AT COMPLETION |  |  | MILESTONES ACHIEVED |  |  | OVERALL RAG
53.42% |  | 0.94278 |  |  |  | 0.9624 |  |  |  | 105.6 |  |  | 2 / 5 |  |  | AMBER
Planned: 57% |  | Slightly behind |  |  |  | Minor overrun |  |  |  | EAC: ₹109.7 L |  |  | Next: Application integrations |  |  | Based on SPI & CPI thresholds
FORECAST FINISH |  | WORKING DAYS ELAPSED |  |  |  | ACTIVITIES COMPLETE |  |  |  | BEHIND / OVERDUE |  |  | OPEN HIGH RISKS |  |  | COST VARIANCE (CV)
2027-03-12 |  | 61 |  |  |  | 27 |  |  |  | 5 |  |  | 2 |  |  | -2.204
Baseline: 12-Mar-27 |  | of 100 total · 61% |  |  |  | of 51 activities |  |  |  | Activities needing attention |  |  | of 10 active risks |  |  | EV ₹56.4 L vs AC ₹58.6 L
KEY HIGHLIGHTS | [9 empty] | ISSUES, RISKS & ACTIONS
✔ M1 Architecture approved and M2 AI Assistant MVP delivered | [9 empty] | ✖ Oracle sandbox access delayed ~2 weeks — M3 re-forecast; escalated to sponsor
✔ Foundry IQ retrieval at 88% recall@5 on a 250-question benchmark (target 85%) | [9 empty] | ✖ SAP connector effort over estimate — CPI below 1.0; recovery plan in Month 4
✔ SAP and QA/testing connectors running end-to-end in non-production | [9 empty] | ! GPT-5 TPM quota limits load tests — increase requested with Microsoft
✔ P95 response time 6.4 s at 50 concurrent users (target ≤ 8 s) | [9 empty] | ! Groundedness 87% vs 90% target — prompt & citation tuning in sprint S7
► Next 2 weeks: Entra ID RBAC, authorization rules, AI evaluation sprint | [9 empty] | ► Decision needed: approve 1-week M3 slip or descope Oracle write-back demo
1 · EARNED VALUE — PV vs EV vs AC | [9 empty] | 2 · PERFORMANCE INDICES TREND
3 · PHASE TIMELINE | [9 empty] | 4 · PHASE PROGRESS
5 · COST PERFORMANCE | [9 empty] | 6 · ACTIVITY STATUS
7 · RESOURCE LOADING | [9 empty] | 8 · BURNDOWN
9 · AI QUALITY KPIs | [9 empty] | 10 · RAID SUMMARY
11 · RISK EXPOSURE | [9 empty] | 12 · RISK RATING MIX
13 · RISK HEAT MAP (count of active risks) | [9 empty] | 14 · MILESTONE TRACKER
Probability ↓ / Impact → | 1 | 2 |  | 3 |  | 4 |  | 5 |  | ID | Milestone |  |  | Baseline | Forecast |  | Status | Var (d)
5 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | M1 | Architecture approved |  |  | 2026-11-16 | 2026-11-16 |  | Achieved | 0
4 | 0 | 0 |  | 1 |  | 0 |  | 1 |  | M2 | AI assistant MVP |  |  | 2026-12-15 | 2026-12-14 |  | Achieved | -1
3 | 0 | 0 |  | 0 |  | 3 |  | 1 |  | M3 | Application integrations |  |  | 2027-01-14 | 2027-01-22 |  | At Risk | 6
2 | 0 | 0 |  | 2 |  | 1 |  | 1 |  | M4 | Release candidate |  |  | 2027-02-12 | 2027-02-16 |  | At Risk | 2
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | M5 | Pilot accepted |  |  | 2027-03-12 | 2027-03-12 |  | On Track | 0
15 · PHASE SUMMARY
Phase |  |  | Start |  | Finish |  | Budget ₹ L |  | EV ₹ L |  | AC ₹ L | CPI |  | Planned % | Actual % |  | Status
M1 Discovery |  |  | 2026-10-19 |  | 2026-11-16 |  | 16.96 |  | 16.96 |  | 16.26 | 1.0431 |  | 100% | 100% |  | Complete
M2 AI Foundation |  |  | 2026-11-17 |  | 2026-12-15 |  | 17.28 |  | 17.28 |  | 17.9 | 0.96536 |  | 100% | 100% |  | Complete
M3 Integration |  |  | 2026-12-16 |  | 2027-01-14 |  | 23.68 |  | 20 |  | 22.28 | 0.89767 |  | 100% | 84.46% |  | Overdue
M4 Security & QA |  |  | 2027-01-15 |  | 2027-02-12 |  | 23.68 |  | 2.176 |  | 2.18 | 0.99817 |  | 8.108% | 9.189% |  | In Progress
M5 Pilot & Handover |  |  | 2027-02-15 |  | 2027-03-12 |  | 24 |  | 0 |  | 0 | 1 |  | 0% | 0% |  | Not Started
Total project |  |  | 2026-10-19 |  | 2027-03-12 |  | 105.6 |  | 56.416 |  | 58.62 | 0.9624 |  | 56.67% | 53.42% |  | In Progress
Demo data for illustration · Blue cells on other sheets are inputs · Change Status Date on 'Project Setup' to roll the dashboard forward

## Project Setup
Project Setup & Parameters
Blue cells are inputs; every sheet calculates from these values
Parameter | Value | Named range | Notes
Project name | Vodafone–VOIS Intelligent AI Assistant
Client / business unit | Vodafone Intelligent Solutions (VOIS)
Project code | VOIS-GENAI-2026-014
Project type | Enterprise Generative AI · RAG · MCP integration
Target platform | Microsoft Azure AI Foundry (GPT-5, Foundry IQ)
Azure region (demo) | West Europe
Delivery methodology | Agile Scrum — 2-week sprints, monthly phase gates
Executive sponsor | Rajesh Menon — Head of Enterprise Applications
Project manager | Ananya Rao — PMP, PMI-ACP
Product owner | Vikram Desai — IT Service Excellence
Project Start (Monday) | 2026-10-19 | ProjectStart | Assumed kickoff date for the demo
Status Date (data date) | 2027-01-15 | StatusDate | Progress is reported as at this date (Week 13)
Blended daily rate (₹ L / person-day) | 0.32 | BlendedRate | Demo assumption — blended onshore/offshore rate
Management reserve (% of BAC) | 10% | MgmtReserve
Sprint length (calendar days) | 14 | SprintLen
Currency / unit | ₹ Lakh (1 L = ₹100,000)

## WBS Schedule
Vodafone–VOIS Intelligent AI Assistant — Work Breakdown Structure, Schedule & Earned Value
Dates calculate from Project Start, predecessors and Holidays · Blue cells are inputs · Values in ₹ Lakh
Project Start: |  | 2026-10-19 | Status Date: | 2027-01-15
Gantt: black = project · grey = phase · red = activity in progress/planned · green = complete · ◆ = milestone · yellow column = status week | [20 empty] | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | +1
[21 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
WBS ID | Level | Work Package / Activity | Deliverable | Responsible | Predecessors | Duration (work days) | Start | Finish | Planned % | Actual % | Variance | Status | FTE | Effort (person-days) | Budget (BAC ₹ L) | Planned Value (PV ₹ L) | Earned Value (EV ₹ L) | Actual Cost (AC ₹ L) | Sprint | Notes / Exit Criteria | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08
0 | 0 | Vodafone–VOIS Intelligent AI Assistant (Pilot) | Security-reviewed, deployment-ready pilot | Project Manager / Product Owner |  | 100 | 2026-10-19 | 2027-03-12 | 56.67% | 53.42% | -3.242% | In Progress |  | 330 | 105.6 | 59.84 | 56.416 | 58.62 |  | Full enterprise rollout across all SAP/Oracle/testing apps is a subsequent phase | bar: 2026-10-19 to 2027-03-08
1 | 1 | Month 1 — Discovery, Requirements & Architecture | Milestone M1: Architecture approved | Project Manager |  | 20 | 2026-10-19 | 2026-11-16 | 100% | 100% | 0% | Complete | 3 | 53 | 16.96 | 16.96 | 16.96 | 16.26 |  | Exit: Stakeholders approve the MVP scope, architecture, security approach, initial use cases and access requirements. | bar: 2026-10-19 to 2026-11-16
1.1 | 2 | Project kickoff, objectives and stakeholder identification | Project charter | Project Manager |  | 2 | 2026-10-19 | 2026-10-20 | 100% | 100% | 0% | Complete | 3 | 6 | 1.92 | 1.92 | 1.92 | 1.84 | S1 | bar: 2026-10-19
1.2 | 2 | Identify user personas: employees, QA, IT support, business users | Persona catalogue | Product Owner | 1.1 | 2 | 2026-10-21 | 2026-10-22 | 100% | 100% | 0% | Complete | 2 | 4 | 1.28 | 1.28 | 1.28 | 1.23 | S1 | bar: 2026-10-19
1.3 | 2 | Gather SAP, Oracle, QA and testing use cases | Use-case catalogue | Product Owner / App SMEs | 1.1 | 3 | 2026-10-21 | 2026-10-23 | 100% | 100% | 0% | Complete | 3 | 9 | 2.88 | 2.88 | 2.88 | 2.76 | S1 | bar: 2026-10-19
1.4 | 2 | Define functional and non-functional requirements | Requirements specification | Product Owner | 1.3 | 3 | 2026-10-26 | 2026-10-28 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.84 | S1 | bar: 2026-10-26
1.5 | 2 | Inventory available APIs, MCP-capable tools and documentation | Application inventory | Backend / MCP Engineer | 1.3 | 3 | 2026-10-26 | 2026-10-28 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.84 | S1 | bar: 2026-10-26
1.6 | 2 | Assess document quality, data classification and source ownership | Data-source assessment | AI / RAG Engineer / App SMEs | 1.5 | 3 | 2026-10-29 | 2026-11-02 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.84 | S1 | bar: 2026-10-26 to 2026-11-02
1.7 | 2 | Design Azure AI Foundry and application architecture | Architecture diagram | Solution Architect | 1.4 | 3 | 2026-10-29 | 2026-11-02 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.84 | S1 | bar: 2026-10-26 to 2026-11-02
1.8 | 2 | Define RAG, Foundry IQ and MCP interaction patterns | Integration design | Solution Architect | 1.7, 1.6 | 2 | 2026-11-03 | 2026-11-04 | 100% | 100% | 0% | Complete | 2 | 4 | 1.28 | 1.28 | 1.28 | 1.23 | S2 | bar: 2026-11-02
1.9 | 2 | Design identity, access, network and secrets management | Security design | Security Engineer | 1.7 | 2 | 2026-11-03 | 2026-11-04 | 100% | 100% | 0% | Complete | 1 | 2 | 0.64 | 0.64 | 0.64 | 0.61 | S2 | bar: 2026-11-02
1.10 | 2 | Create backlog, sprint plan, risks and acceptance criteria | Delivery plan | Project Manager | 1.8, 1.9 | 2 | 2026-11-05 | 2026-11-06 | 100% | 100% | 0% | Complete | 2 | 4 | 1.28 | 1.28 | 1.28 | 1.23 | S2 | bar: 2026-11-02
M1 | 2 | ◆ Milestone M1 — Architecture approved | Signed-off requirements and design | Project Manager / Sponsor | End of Week 4 | 0 | 2026-11-16 | 2026-11-16 | 100% | 100% | 0% | Complete | [6 empty] | S3 | Gate: all phase deliverables complete before sign-off | bar: 2026-11-16
2 | 1 | Month 2 — AI Foundation & Knowledge Retrieval | Milestone M2: AI assistant MVP | Project Manager |  | 20 | 2026-11-17 | 2026-12-15 | 100% | 100% | 0% | Complete | 3 | 54 | 17.28 | 17.28 | 17.28 | 17.9 |  | Exit: A user can ask questions about approved sample documentation and receive relevant, source-grounded answers through the chat interface. | bar: 2026-11-16 to 2026-12-14
2.1 | 2 | Provision approved Azure development resources | Development environment | DevOps Engineer | M1 | 2 | 2026-11-17 | 2026-11-18 | 100% | 100% | 0% | Complete | 1 | 2 | 0.64 | 0.64 | 0.64 | 0.65 | S3 | bar: 2026-11-16
2.2 | 2 | Configure AI Foundry project and model access | Foundry environment | AI / RAG Engineer | 2.1 | 2 | 2026-11-19 | 2026-11-20 | 100% | 100% | 0% | Complete | 2 | 4 | 1.28 | 1.28 | 1.28 | 1.31 | S3 | bar: 2026-11-16
2.3 | 2 | Validate GPT-5 availability, deployment and inference | Model integration | AI / RAG Engineer | 2.2 | 2 | 2026-11-23 | 2026-11-25 | 100% | 100% | 0% | Complete | 2 | 4 | 1.28 | 1.28 | 1.28 | 1.31 | S3 | bar: 2026-11-23
2.4 | 2 | Evaluate GPT_Image-2 availability and visual-generation use cases | Image capability proof of concept | AI / RAG Engineer | 2.3 | 1 | 2026-11-26 | 2026-11-26 | 100% | 100% | 0% | Complete | 1 | 1 | 0.32 | 0.32 | 0.32 | 0.33 | S3 | bar: 2026-11-23
2.5 | 2 | Prepare sample SAP, Oracle, QA and testing documents | Curated test corpus | App SMEs / AI / RAG Engineer | M1 | 3 | 2026-11-17 | 2026-11-19 | 100% | 100% | 0% | Complete | 3 | 9 | 2.88 | 2.88 | 2.88 | 2.94 | S3 | bar: 2026-11-16
2.6 | 2 | Configure Foundry IQ knowledge sources and retrieval | Knowledge retrieval pipeline | AI / RAG Engineer | 2.3, 2.5 | 4 | 2026-11-26 | 2026-12-01 | 100% | 100% | 0% | Complete | 2 | 8 | 2.56 | 2.56 | 2.56 | 2.87 | S3 | bar: 2026-11-23 to 2026-11-30
2.7 | 2 | Implement chunking, indexing and metadata strategy | Searchable knowledge base | AI / RAG Engineer | 2.6 | 3 | 2026-12-02 | 2026-12-04 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.96 | S4 | bar: 2026-11-30
2.8 | 2 | Implement grounded answers, citations and source references | RAG response workflow | AI / RAG Engineer | 2.7 | 3 | 2026-12-07 | 2026-12-09 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.96 | S4 | bar: 2026-12-07
2.9 | 2 | Build chat UI, conversation flow and application navigation | Web chat prototype | Frontend Engineer | 2.3 | 4 | 2026-11-26 | 2026-12-01 | 100% | 100% | 0% | Complete | 2 | 8 | 2.56 | 2.56 | 2.56 | 2.61 | S3 | bar: 2026-11-23 to 2026-11-30
2.10 | 2 | Add logging, error handling and baseline evaluation | Baseline evaluation report | QA Engineer / AI / RAG Engineer | 2.8, 2.9 | 3 | 2026-12-10 | 2026-12-14 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 1.96 | S4 | bar: 2026-12-07 to 2026-12-14
M2 | 2 | ◆ Milestone M2 — AI assistant MVP | Grounded answers from approved documents | Project Manager / Sponsor | End of Week 8 | 0 | 2026-12-15 | 2026-12-15 | 100% | 100% | 0% | Complete | [6 empty] | S5 | Gate: all phase deliverables complete before sign-off | bar: 2026-12-14
3 | 1 | Month 3 — MCP & Enterprise Integration | Milestone M3: Application integrations | Project Manager |  | 20 | 2026-12-16 | 2027-01-14 | 100% | 84.46% | -15.54% | Overdue | 3 | 74 | 23.68 | 23.68 | 20 | 22.28 |  | Exit: The assistant answers knowledge questions and executes approved, read-only operations against available test integrations (SAP/Oracle scope subject to API access, licensing and environment readiness). | bar: 2026-12-14 to 2027-01-11
3.1 | 2 | Define MCP server/client architecture and tool contracts | MCP design specification | Backend / MCP Engineer | M2 | 3 | 2026-12-16 | 2026-12-18 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 2 | S5 | bar: 2026-12-14
3.2 | 2 | Implement MCP connection and authentication | Working MCP connection | Backend / MCP Engineer | 3.1 | 4 | 2026-12-21 | 2026-12-24 | 100% | 100% | 0% | Complete | 2 | 8 | 2.56 | 2.56 | 2.56 | 2.76 | S5 | bar: 2026-12-21
3.3 | 2 | Develop application discovery and status-query tools | Read-only tool set | Backend / MCP Engineer | 3.2 | 3 | 2026-12-28 | 2026-12-30 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 2 | S6 | bar: 2026-12-28
3.4 | 2 | Integrate SAP through approved APIs or connectors | SAP integration proof of concept | Backend / MCP Engineer / SAP SME | 3.2 | 4 | 2026-12-28 | 2026-12-31 | 100% | 100% | 0% | Complete | 3 | 12 | 3.84 | 3.84 | 3.84 | 4.53 | S6 | bar: 2026-12-28
3.5 | 2 | Integrate Oracle through approved APIs or connectors | Oracle integration proof of concept | Backend / MCP Engineer / Oracle SME | 3.2 | 4 | 2026-12-28 | 2026-12-31 | 100% | 70% | -30% | Overdue | 3 | 12 | 3.84 | 3.84 | 2.688 | 3.63 | S6 | bar: 2026-12-28
3.6 | 2 | Integrate QA and testing application interfaces | QA/testing connector | Backend / MCP Engineer / QA SME | 3.2 | 4 | 2026-12-28 | 2026-12-31 | 100% | 100% | 0% | Complete | 2 | 8 | 2.56 | 2.56 | 2.56 | 2.66 | S6 | bar: 2026-12-28
3.7 | 2 | Implement tool selection and parameter validation | Tool-routing workflow | AI / RAG Engineer | 3.3 | 3 | 2026-12-31 | 2027-01-05 | 100% | 100% | 0% | Complete | 2 | 6 | 1.92 | 1.92 | 1.92 | 2 | S6 | bar: 2026-12-28 to 2027-01-04
3.8 | 2 | Add permission checks, timeouts, retries and error responses | Resilient integration layer | Backend / MCP Engineer | 3.4, 3.5, 3.6 | 3 | 2027-01-04 | 2027-01-06 | 100% | 60% | -40% | Overdue | 2 | 6 | 1.92 | 1.92 | 1.152 | 1.2 | S6 | bar: 2027-01-04
3.9 | 2 | Test retrieval-plus-tool workflows end to end | Integration test report | QA Engineer | 3.7, 3.8 | 3 | 2027-01-07 | 2027-01-11 | 100% | 50% | -50% | Overdue | 3 | 9 | 2.88 | 2.88 | 1.44 | 1.5 | S6 | bar: 2027-01-04 to 2027-01-11
3.10 | 2 | Add traceable tool execution summaries | Tool audit records | Backend / MCP Engineer | 3.9 | 1 | 2027-01-12 | 2027-01-12 | 100% | 0% | -100% | Overdue | 1 | 1 | 0.32 | 0.32 | 0 | 0 | S7 | bar: 2027-01-11
M3 | 2 | ◆ Milestone M3 — Application integrations | Demonstrable end-to-end test workflows | Project Manager / Sponsor | End of Week 12 | 0 | 2027-01-14 | 2027-01-14 | 100% | 0% | -100% | Overdue | [6 empty] | S7 | Gate: all phase deliverables complete before sign-off | bar: 2027-01-11
4 | 1 | Month 4 — Security, Testing & Quality | Milestone M4: Release candidate | Project Manager |  | 20 | 2027-01-15 | 2027-02-12 | 8.108% | 9.189% | 1.081% | In Progress | 4 | 74 | 23.68 | 1.92 | 2.176 | 2.18 |  | Exit: Critical security and functional defects are resolved, agreed evaluation thresholds are met, and release risks are documented. | bar: 2027-01-11 to 2027-02-08
4.1 | 2 | Configure Microsoft Entra ID authentication and role-based access | Identity and role controls | Security Engineer | M3 | 3 | 2027-01-15 | 2027-01-19 | 33.33% | 30% | -3.333% | In Progress | 2 | 6 | 1.92 | 0.64 | 0.576 | 0.58 | S7 | bar: 2027-01-11 to 2027-01-18
4.2 | 2 | Configure secrets management and secure configuration | Secrets-management setup | DevOps Engineer | M3 | 2 | 2027-01-15 | 2027-01-18 | 50% | 100% | 50% | Complete | 1 | 2 | 0.64 | 0.32 | 0.64 | 0.64 | S7 | bar: 2027-01-11 to 2027-01-18
4.3 | 2 | Enforce source-level and application-level authorization | Access-control validation | Security Engineer / Backend Engineer | 4.1 | 4 | 2027-01-20 | 2027-01-25 | 0% | 0% | 0% | Not Started | 2 | 8 | 2.56 | 0 | 0 | 0 | S7 | bar: 2027-01-18 to 2027-01-25
4.4 | 2 | Test prompt injection, data leakage and unsafe tool requests | AI security test report | Security Engineer | 4.3 | 3 | 2027-01-27 | 2027-01-29 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S8 | bar: 2027-01-25
4.5 | 2 | Evaluate answer correctness, grounding and citation quality | AI evaluation report | AI / RAG Engineer / QA Engineer | M3 | 4 | 2027-01-15 | 2027-01-20 | 25% | 25% | 0% | In Progress | 3 | 12 | 3.84 | 0.96 | 0.96 | 0.96 | S7 | bar: 2027-01-11 to 2027-01-18
4.6 | 2 | Validate QA scenarios, edge cases and negative paths | Functional QA report | QA Engineer | 4.5 | 3 | 2027-01-21 | 2027-01-25 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S7 | bar: 2027-01-18 to 2027-01-25
4.7 | 2 | Test regression, integration and tool-call consistency | Regression suite | QA Engineer | 4.6 | 3 | 2027-01-27 | 2027-01-29 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S8 | bar: 2027-01-25
4.8 | 2 | Measure response time, concurrency and failure recovery | Performance report | QA Engineer / DevOps Engineer | 4.7 | 3 | 2027-02-01 | 2027-02-03 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S8 | bar: 2027-02-01
4.9 | 2 | Implement monitoring, tracing, audit logs and alerts | Observability dashboard | DevOps Engineer | 4.2 | 3 | 2027-01-19 | 2027-01-21 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S7 | bar: 2027-01-18
4.10 | 2 | Resolve defects and prepare the release candidate | Release candidate | Engineering Team | 4.4, 4.8, 4.9 | 4 | 2027-02-04 | 2027-02-09 | 0% | 0% | 0% | Not Started | 4 | 16 | 5.12 | 0 | 0 | 0 | S8 | bar: 2027-02-01 to 2027-02-08
M4 | 2 | ◆ Milestone M4 — Release candidate | Security, QA and evaluation reports | Project Manager / Sponsor | End of Week 16 | 0 | 2027-02-12 | 2027-02-12 | 0% | 0% | 0% | Not Started | [6 empty] | S9 | Gate: all phase deliverables complete before sign-off | bar: 2027-02-08
5 | 1 | Month 5 — UAT, Pilot, Deployment & Handover | Milestone M5: Pilot accepted | Project Manager |  | 20 | 2027-02-15 | 2027-03-12 | 0% | 0% | 0% | Not Started | 4 | 75 | 24 | 0 | 0 | 0 |  | Exit: Business stakeholders accept the pilot results, operational ownership is assigned, and production deployment is approved or has a documented readiness decision. | bar: 2027-02-15 to 2027-03-08
5.1 | 2 | Prepare UAT scenarios and business acceptance criteria | UAT plan | Product Owner | M4 | 2 | 2027-02-15 | 2027-02-16 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S9 | bar: 2027-02-15
5.2 | 2 | Conduct employee, QA and IT support user acceptance testing | UAT results | QA Engineer / Business Users | 5.1 | 4 | 2027-02-17 | 2027-02-22 | 0% | 0% | 0% | Not Started | 4 | 16 | 5.12 | 0 | 0 | 0 | S9 | bar: 2027-02-15 to 2027-02-22
5.3 | 2 | Validate SAP, Oracle and QA workflows with system owners | Business validation report | App SMEs / System Owners | 5.1 | 3 | 2027-02-17 | 2027-02-19 | 0% | 0% | 0% | Not Started | 3 | 9 | 2.88 | 0 | 0 | 0 | S9 | bar: 2027-02-15
5.4 | 2 | Collect pilot feedback and prioritize defects | Feedback backlog | Product Owner | 5.2, 5.3 | 2 | 2027-02-23 | 2027-02-24 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S10 | bar: 2027-02-22
5.5 | 2 | Fix defects and perform final regression testing | Approved build | Engineering Team | 5.4 | 4 | 2027-02-25 | 2027-03-02 | 0% | 0% | 0% | Not Started | 4 | 16 | 5.12 | 0 | 0 | 0 | S10 | bar: 2027-02-22 to 2027-03-01
5.6 | 2 | Prepare CI/CD pipeline and deployment configuration | Deployment pipeline | DevOps Engineer | M4 | 3 | 2027-02-15 | 2027-02-17 | 0% | 0% | 0% | Not Started | 2 | 6 | 1.92 | 0 | 0 | 0 | S9 | bar: 2027-02-15
5.7 | 2 | Validate environment configuration, access and rollback procedure | Deployment checklist | DevOps Engineer | 5.5, 5.6 | 2 | 2027-03-03 | 2027-03-04 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S10 | bar: 2027-03-01
5.8 | 2 | Deploy to the approved pilot environment | Pilot deployment | DevOps Engineer | 5.7 | 2 | 2027-03-05 | 2027-03-08 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S10 | bar: 2027-03-01 to 2027-03-08
5.9 | 2 | Conduct user onboarding and operational training | User and operator guides | Project Manager / Trainer | 5.8 | 2 | 2027-03-09 | 2027-03-10 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S11 | bar: 2027-03-08
5.10 | 2 | Complete architecture, support and technical handover | Handover package | Solution Architect | 5.8 | 2 | 2027-03-09 | 2027-03-10 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S11 | bar: 2027-03-08
5.11 | 2 | Review KPIs, acceptance criteria and outstanding risks | Final project report | Project Manager | 5.9, 5.10 | 2 | 2027-03-11 | 2027-03-12 | 0% | 0% | 0% | Not Started | 2 | 4 | 1.28 | 0 | 0 | 0 | S11 | bar: 2027-03-08
M5 | 2 | ◆ Milestone M5 — Pilot accepted | UAT sign-off and handover | Project Manager / Sponsor | End of Week 20 | 0 | 2027-03-12 | 2027-03-12 | 0% | 0% | 0% | Not Started | [6 empty] | S11 | Gate: all phase deliverables complete before sign-off | bar: 2027-03-08

## Milestones
Milestones & Phase Gates
Baseline = end of each 4-week month · Forecast and Actual dates are inputs
ID | Milestone | Target Week | Baseline Date | Forecast Date | Actual Date | Variance (work days) | Status | Acceptance Evidence | Exit Criteria
M1 | Architecture approved | Week 4 | 2026-11-16 | 2026-11-16 | 2026-11-16 | 0 | Achieved | Signed-off requirements and design | Stakeholders approve the MVP scope, architecture, security approach, initial use cases and access requirements.
M2 | AI assistant MVP | Week 8 | 2026-12-15 | 2026-12-15 | 2026-12-14 | -1 | Achieved | Grounded answers from approved documents | A user can ask questions about approved sample documentation and receive relevant, source-grounded answers through the chat interface.
M3 | Application integrations | Week 12 | 2027-01-14 | 2027-01-22 |  | 6 | At Risk | Demonstrable end-to-end test workflows | The assistant answers knowledge questions and executes approved, read-only operations against available test integrations (SAP/Oracle scope subject to API access, licensing and environment readiness).
M4 | Release candidate | Week 16 | 2027-02-12 | 2027-02-16 |  | 2 | At Risk | Security, QA and evaluation reports | Critical security and functional defects are resolved, agreed evaluation thresholds are met, and release risks are documented.
M5 | Pilot accepted | Week 20 | 2027-03-12 | 2027-03-12 |  | 0 | On Track | UAT sign-off and handover | Business stakeholders accept the pilot results, operational ownership is assigned, and production deployment is approved or has a documented readiness decision.
Formulas:
Variance (work days) = IF([Actual Date]<>"",IF([Actual Date]>[Baseline Date],NETWORKDAYS([Baseline Date],[Actual Date],Holidays)-1,-(NETWORKDAYS([Actual Date],[Baseline Date],Holidays)-1)),IF([Forecast Date]>[Baseline Date],NETWORKDAYS([Baseline Date],[Forecast Date],Holidays)-1,-(NETWORKDAYS([Forecast Date],[Baseline Date],Holidays)-1)))

## Team & Resources
Team Structure & Resourcing
Blue values are editable · Cost = Headcount × Allocation × Rate × Working days
Role | Named Resources (demo) | Headcount | Allocation (FTE %) | Day Rate (₹ L) | Effective FTE | Cost over Project (₹ L) | Responsibilities
Project Manager / Product Owner | Ananya Rao; Vikram Desai | 2 | 100% | 0.42 | 2 | 84 | Scope, priorities, stakeholders, risks and acceptance
Solution Architect | Karthik Iyer | 1 | 60% | 0.45 | 0.6 | 27 | Architecture decisions, integration contracts, handover
AI / RAG Engineer | Priya Nair; Arjun Mehta | 2 | 100% | 0.36 | 2 | 72 | GPT-5, Foundry IQ, prompts, retrieval and evaluation
Backend / MCP Engineer | Rohan Kulkarni; Sneha Joshi | 2 | 100% | 0.32 | 2 | 64 | MCP tools, APIs, application connectors and orchestration
Frontend Engineer | Meera Pillai | 1 | 100% | 0.28 | 1 | 28 | Chat UI, application dashboard and user experience
QA Engineer | Divya Shetty | 1 | 100% | 0.26 | 1 | 26 | Test strategy, evaluation datasets, regression and UAT support
Security Engineer | Aditya Bose | 1 | 50% | 0.38 | 0.5 | 19 | Entra ID, authorization, AI security testing
DevOps Engineer | Farhan Qureshi | 1 | 80% | 0.3 | 0.8 | 24 | Azure provisioning, CI/CD, observability
SAP / Oracle / QA Application SMEs | SAP CoE; Oracle DBA team; QA tooling owners | 3 | 25% | 0.35 | 0.75 | 26.25 | Use cases, API access, business validation
Total |  | 14 |  |  | 10.65 | 370.25 | Core team of ~10 named members plus shared SMEs (source plan: 7–10 core)

## Workstreams
Cross-Functional Workstreams
Activities that span multiple phases; Start/End week are inputs
Workstream | Lead | Start Week | End Week | Key Outputs | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
Project management | Ananya Rao | 1 | 20 | Sprint reviews, RAID log, status reports | bar: W1 to W20
Architecture and engineering | Karthik Iyer | 1 | 20 | Architecture decisions, integration contracts | bar: W1 to W20
Data and knowledge engineering | Priya Nair | 2 | 12 | Curated content, retrieval quality | bar: W2 to W12
AI and prompt engineering | Arjun Mehta | 5 | 16 | System instructions, grounded response flows | bar: W5 to W16
MCP and API integration | Rohan Kulkarni | 8 | 14 | Tool servers, connectors, error handling | bar: W8 to W14
Security and responsible AI | Aditya Bose | 1 | 20 | Access reviews, threat assessments, auditability | bar: W1 to W20
QA and evaluation | Divya Shetty | 5 | 20 | Test suites, evaluation datasets, defect reports | bar: W5 to W20
DevOps and observability | Farhan Qureshi | 2 | 20 | CI/CD, telemetry, alerts, deployment procedures | bar: W2 to W20
Change management | Ananya Rao | 16 | 20 | Training, user feedback, support handover | bar: W16 to W20

## RACI
RACI Matrix
R = Responsible · A = Accountable · C = Consulted · I = Informed
WBS Ref | Deliverable Group | Project Manager / PO | Solution Architect | AI / RAG Engineer | Backend / MCP Engineer | Frontend Engineer | QA Engineer | Security Engineer | DevOps Engineer | App SMEs (SAP/Oracle/QA) | Business Sponsor
1.1–1.4 | Charter, personas, use cases & requirements | A/R | C | C | C | I | C | C | I | R | A
1.5–1.6 | Application inventory & data-source assessment | A | C | R | R | I | I | C | I | R | I
1.7–1.8 | Solution architecture & RAG/MCP integration design | A | R | C | C | C | I | C | C | C | I
1.9 | Security design (identity, network, secrets) | A | C | I | C | I | I | R | C | I | I
2.1–2.4 | Azure / AI Foundry environment & model integration | A | C | R | I | I | I | C | R | I | I
2.5–2.8 | Knowledge corpus, retrieval & grounded answers | A | C | R | I | I | C | I | I | R | I
2.9 | Chat UI prototype | A | C | C | C | R | C | I | I | I | C
3.1–3.3 | MCP architecture, connection & read-only tools | A | C | C | R | I | C | C | I | I | I
3.4–3.6 | SAP / Oracle / QA connectors | A | C | I | R | I | C | C | I | R | I
3.7–3.10 | Tool routing, resilience & audit trail | A | C | R | R | I | R | C | I | I | I
4.1–4.4 | Identity, authorization & AI security testing | A | C | C | C | I | C | R | R | I | I
4.5–4.8 | AI evaluation, functional, regression & performance testing | A | I | R | C | C | R | I | C | C | I
4.9–4.10 | Observability & release candidate | A | C | R | R | R | R | C | R | I | I
5.1–5.5 | UAT, business validation & defect resolution | A/R | C | R | R | R | R | C | C | R | A
5.6–5.8 | CI/CD & pilot deployment | A | C | C | C | I | C | C | R | I | I
5.9–5.11 | Training, handover & final report | A/R | R | C | C | C | C | C | C | C | A

## KPIs
KPIs & Success Measures
Demo values · Attainment = Current vs Target (capped at 120%) · Green ≥ 100%, Amber ≥ 90%, Red < 90%
KPI | Definition | Measurement Method | Direction | Baseline | Target | Current | Attainment | RAG | Trend | Owner
Answer groundedness | % of answers fully supported by retrieved sources | LLM-as-judge + human review, 250-question benchmark | Higher | 72% | 90% | 87% | 96.67% | AMBER | ▲ Improving | Arjun Mehta
Citation correctness | % of citations pointing to the right source passage | Manual audit of 100 sampled answers | Higher | 65% | 95% | 91% | 95.79% | AMBER | ▲ Improving | Priya Nair
Retrieval recall@5 | Relevant document in top-5 results | Benchmark question set vs gold labels | Higher | 64% | 85% | 88% | 103.5% | GREEN | ▲ Improving | Priya Nair
Tool-call success rate | Successful, authorized MCP calls / total | Tool audit records (test environment) | Higher | 90% | 98% | 95.5% | 97.45% | AMBER | ▲ Improving | Rohan Kulkarni
Unauthorized data access | Incidents in defined security test scenarios | Security test suite incl. prompt injection | Lower | 0 | 0 | 0 | 100% | GREEN | ► Stable | Aditya Bose
P95 response time (s) | End-to-end latency at pilot concurrency | Load test, 50 concurrent users | Lower | 11.2 | 8 | 6.4 | 100% | GREEN | ▲ Improving | Farhan Qureshi
User satisfaction (CSAT) | Average rating from demo/pilot users (1–5) | In-app feedback + pilot survey | Higher | 3.1 | 4 | 4.2 | 105% | GREEN | ▲ Improving | Vikram Desai
Manual lookup effort reduction | Reduction in time spent searching documentation | Time-and-motion study, QA & IT support | Higher | 0% | 40% | 32% | 80% | RED | ▲ Improving | Vikram Desai

## RAID Log
RAID Log — Risks, Assumptions, Issues & Dependencies
Score = Probability × Impact (1–5): High ≥ 15 · Medium 8–14 · Low ≤ 7
ID | Type | Description | Category | Probability (1–5) | Impact (1–5) | Score | Rating | Mitigation / Response | Owner | Status
R-01 | Risk | SAP/Oracle API access, licensing or non-production environments not available in time | Integration | 4 | 5 | 20 | High | Access requests raised Week 1; mock services; reduced M3 scope agreed if needed | Ananya Rao | Open
R-02 | Risk | GPT-5, GPT_Image-2 or Foundry IQ not available/configurable in the target Azure region | Technology | 2 | 4 | 8 | Medium | Availability validated in Week 6; fallback model identified; GPT_Image-2 optional | Arjun Mehta | Mitigated
R-03 | Risk | Poor document quality or unclear source ownership degrades retrieval and grounding | Data | 3 | 4 | 12 | Medium | Data-source assessment; curated corpus; content owners named per source | Priya Nair | Monitoring
R-04 | Risk | Confidential production data ingested into development environment | Security | 2 | 5 | 10 | Medium | Approved sample data only; classification gate before ingestion | Aditya Bose | Monitoring
R-05 | Risk | Prompt injection or unsafe tool invocation leads to data leakage | Security | 3 | 5 | 15 | High | Read-only MCP tools; parameter validation; permission checks; red-team tests in 4.4 | Aditya Bose | Open
R-06 | Risk | Hallucination / evaluation thresholds not met by release candidate | Quality | 3 | 4 | 12 | Medium | Baseline evaluation Month 2; prompt & retrieval tuning; citation enforcement | Arjun Mehta | Open
R-07 | Risk | Part-time SME availability delays validation and UAT | Resourcing | 4 | 3 | 12 | Medium | Fixed weekly SME slots; escalation via sponsor | Ananya Rao | Open
R-08 | Risk | Scope creep into write operations or additional applications | Scope | 3 | 4 | 12 | Medium | Change control; write operations need separate security review | Vikram Desai | Monitoring
R-09 | Risk | Response-time or concurrency targets not achieved | Performance | 2 | 3 | 6 | Low | Early performance spike; caching; deployment sizing | Farhan Qureshi | Mitigated
R-10 | Risk | Low pilot adoption limits feedback and business case | Change | 2 | 3 | 6 | Low | Lead with QA & Testing Assistant use case; onboarding and training | Vikram Desai | Open
I-01 | Issue | Oracle non-production sandbox access delayed ~2 weeks by licensing approval | Integration | 5 | 4 | 20 | High | Escalated to sponsor 06-Jan; mock Oracle service used; M3 re-forecast | Ananya Rao | Open
I-02 | Issue | GPT-5 tokens-per-minute quota limits load testing | Technology | 4 | 3 | 12 | Medium | Quota increase requested with Microsoft; tests throttled meanwhile | Farhan Qureshi | Open
I-03 | Issue | SAP connector effort above estimate (custom BAPI wrapper needed) | Integration | 5 | 2 | 10 | Medium | Change absorbed in contingency; CPI recovery plan for Month 4 | Rohan Kulkarni | Monitoring
A-01 | Assumption | MVP uses read-only MCP tools only | Scope |  |  |  |  | Validated at M1 sign-off | Vikram Desai | Closed
A-02 | Assumption | Pilot scope is a limited set of high-value SAP, Oracle and QA use cases | Scope |  |  |  |  | Confirmed in requirements (1.4) | Vikram Desai | Closed
D-01 | Dependency | Approved non-production application access, API documentation and sample data | Integration |  |  |  |  | Tracked weekly in status meeting | Ananya Rao | Open
D-02 | Dependency | Microsoft Entra ID configuration and identity team support | Security |  |  |  |  | Identity team engaged; slot booked Week 13 | Aditya Bose | Open
D-03 | Dependency | Application-owner support for integration and business validation | Resourcing |  |  |  |  | SME plan agreed at kickoff | Ananya Rao | Monitoring

## Holidays
Non-Working Days
Demo India holiday calendar — confirm against the client's HR calendar · all dates skip these
# | Date | Description
1 | 2026-11-09 | Diwali (demo)
2 | 2026-11-24 | Guru Nanak Jayanti (demo)
3 | 2026-12-25 | Christmas Day
4 | 2027-01-01 | New Year's Day
5 | 2027-01-26 | Republic Day
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Weekly Status Log
Weekly Status Log (EVM)
Cumulative values as reported at each week-end · blue = reported inputs · SPI = EV/PV · CPI = EV/AC
Week | Week Ending | Planned Value (PV ₹ L) | Earned Value (EV ₹ L) | Actual Cost (AC ₹ L) | SPI | CPI | Activities Remaining | RAG | Key Commentary
1 | 2026-10-23 | 6.08 | 6.1 | 6.1 | 1.0033 | 1 | 48 | GREEN | Kickoff held; charter and stakeholder map approved; personas drafted
2 | 2026-10-30 | 12.48 | 12.1 | 12.1 | 0.96955 | 1 | 47 | GREEN | 28 use cases captured across SAP, Oracle, QA; NFR workshop completed
3 | 2026-11-06 | 16.96 | 16.8 | 16.7 | 0.99057 | 1.006 | 42 | GREEN | Requirements spec baselined; API & MCP tool inventory 80% complete
4 | 2026-11-13 | 16.96 | 17 | 16.7 | 1.0024 | 1.018 | 41 | GREEN | Diwali week; architecture and data-source assessment in progress
5 | 2026-11-20 | 21.76 | 22 | 21.8 | 1.011 | 1.0092 | 39 | GREEN | Architecture approved — M1 achieved 16-Nov; Azure dev subscription provisioned
6 | 2026-11-27 | 25.92 | 25.9 | 25.9 | 0.99923 | 1 | 36 | GREEN | GPT-5 deployment validated in West Europe; curated corpus of 1,240 documents ready
7 | 2026-12-04 | 30.4 | 30.4 | 30.7 | 1 | 0.99023 | 34 | GREEN | Foundry IQ indexing complete; first grounded answers with citations demonstrated
8 | 2026-12-11 | 33.6 | 33.9 | 34.6 | 1.0089 | 0.97977 | 32 | GREEN | Chat UI prototype live; baseline evaluation 81% groundedness
9 | 2026-12-18 | 36.16 | 35.8 | 36.9 | 0.99004 | 0.97019 | 31 | GREEN | M2 AI Assistant MVP achieved 14-Dec; MCP architecture and tool contracts agreed
10 | 2026-12-25 | 38.72 | 37.9 | 39.4 | 0.97882 | 0.96193 | 30 | AMBER | MCP auth working; SAP connector needs custom BAPI wrapper (I-03)
11 | 2027-01-01 | 51.52 | 48.9 | 52.3 | 0.94915 | 0.93499 | 27 | AMBER | Holiday week; SAP & QA connectors working; Oracle sandbox access blocked (I-01)
12 | 2027-01-08 | 56.64 | 52.6 | 57.4 | 0.92867 | 0.91638 | 25 | AMBER | Oracle access escalated to sponsor; mock Oracle service used; tool routing done
13 | 2027-01-15 | 59.84 | 56.4 | 58.6 | 0.94251 | 0.96246 | 24 | AMBER | M3 slipped — Oracle integration 70%, E2E tests 50%; Entra ID work started; secrets mgmt done early
14 | 2027-01-22 | 69.44
15 | 2027-01-29 | 74.56
16 | 2027-02-05 | 79.04
17 | 2027-02-12 | 81.6
18 | 2027-02-19 | 91.52
19 | 2027-02-26 | 96.64
20 | 2027-03-05 | 101.12
21 | 2027-03-12 | 105.6

## Chart Data
Chart Data
Calculated series feeding the Dashboard charts — no inputs on this sheet
Week | Week Start | Week End | PV cum (₹ L) | Planned Remaining | FTE: M1 Discovery | FTE: M2 AI Foundation | FTE: M3 Integration | FTE: M4 Security & QA | FTE: M5 Pilot & Handover | Target (1.0) | Week Label
1 | 2026-10-19 | 2026-10-23 | 6.08 | 48 | 8 | 0 | 0 | 0 | 0 | 1 | W1
2 | 2026-10-26 | 2026-10-30 | 12.48 | 46 | 8 | 0 | 0 | 0 | 0 | 1 | W2
3 | 2026-11-02 | 2026-11-06 | 16.96 | 41 | 9 | 0 | 0 | 0 | 0 | 1 | W3
4 | 2026-11-09 | 2026-11-13 | 16.96 | 41 | 0 | 0 | 0 | 0 | 0 | 1 | W4
5 | 2026-11-16 | 2026-11-20 | 21.76 | 38 | 0 | 6 | 0 | 0 | 0 | 1 | W5
6 | 2026-11-23 | 2026-11-27 | 25.92 | 36 | 0 | 7 | 0 | 0 | 0 | 1 | W6
7 | 2026-11-30 | 2026-12-04 | 30.4 | 33 | 0 | 6 | 0 | 0 | 0 | 1 | W7
8 | 2026-12-07 | 2026-12-11 | 33.6 | 32 | 0 | 4 | 0 | 0 | 0 | 1 | W8
9 | 2026-12-14 | 2026-12-18 | 36.16 | 30 | 0 | 2 | 2 | 0 | 0 | 1 | W9
10 | 2026-12-21 | 2026-12-25 | 38.72 | 29 | 0 | 0 | 2 | 0 | 0 | 1 | W10
11 | 2026-12-28 | 2027-01-01 | 51.52 | 25 | 0 | 0 | 12 | 0 | 0 | 1 | W11
12 | 2027-01-04 | 2027-01-08 | 56.64 | 23 | 0 | 0 | 7 | 0 | 0 | 1 | W12
13 | 2027-01-11 | 2027-01-15 | 59.84 | 21 | 0 | 0 | 4 | 6 | 0 | 1 | W13
14 | 2027-01-18 | 2027-01-22 | 69.44 | 17 | 0 | 0 | 0 | 12 | 0 | 1 | W14
15 | 2027-01-25 | 2027-01-29 | 74.56 | 13 | 0 | 0 | 0 | 8 | 0 | 1 | W15
16 | 2027-02-01 | 2027-02-05 | 79.04 | 12 | 0 | 0 | 0 | 6 | 0 | 1 | W16
17 | 2027-02-08 | 2027-02-12 | 81.6 | 11 | 0 | 0 | 0 | 4 | 0 | 1 | W17
18 | 2027-02-15 | 2027-02-19 | 91.52 | 8 | 0 | 0 | 0 | 0 | 11 | 1 | W18
19 | 2027-02-22 | 2027-02-26 | 96.64 | 6 | 0 | 0 | 0 | 0 | 10 | 1 | W19
20 | 2027-03-01 | 2027-03-05 | 101.12 | 4 | 0 | 0 | 0 | 0 | 8 | 1 | W20
21 | 2027-03-08 | 2027-03-12 | 105.6 | 0 | 0 | 0 | 0 | 0 | 8 | 1 | W21
Phase | Planned % | Actual % | Budget (₹ L) | Earned Value (₹ L) | Actual Cost (₹ L) | Start offset (days) | Completed (days) | Remaining (days) | Status
M1 Discovery | 100% | 100% | 16.96 | 16.96 | 16.26 | 0 | 29 | 0 | Complete
M2 AI Foundation | 100% | 100% | 17.28 | 17.28 | 17.9 | 29 | 29 | 0 | Complete
M3 Integration | 100% | 84.46% | 23.68 | 20 | 22.28 | 58 | 25.3378 | 4.6622 | Overdue
M4 Security & QA | 8.108% | 9.189% | 23.68 | 2.176 | 2.18 | 88 | 2.6649 | 26.3351 | In Progress
M5 Pilot & Handover | 0% | 0% | 24 | 0 | 0 | 119 | 0 | 26 | Not Started
Activity Status | Count
Complete | 27
In Progress | 2
Behind | 0
Overdue | 4
Late Start | 0
Not Started | 18
Open Risk Rating | Count
High | 2
Medium | 6
Low | 2
RAID Type | Open | Monitoring | Mitigated | Closed
Risk | 5 | 3 | 2 | 0
Issue | 2 | 1 | 0 | 0
Assumption | 0 | 0 | 0 | 2
Dependency | 2 | 1 | 0 | 0
Helper — cumulative planned value by activity and week (₹ L)
WBS ID | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
1.1 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
1.2 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28
1.3 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88
1.4 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
1.5 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
1.6 | 0 | 1.28 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
1.7 | 0 | 1.28 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
1.8 | 0 | 0 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28
1.9 | 0 | 0 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64
1.10 | 0 | 0 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28
2.1 | 0 | 0 | 0 | 0 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64
2.2 | 0 | 0 | 0 | 0 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28
2.3 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28 | 1.28
2.4 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32
2.5 | 0 | 0 | 0 | 0 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88
2.6 | 0 | 0 | 0 | 0 | 0 | 1.28 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56
2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
2.9 | 0 | 0 | 0 | 0 | 0 | 1.28 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56
2.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
3.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56
3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
3.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84
3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84
3.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56
3.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
3.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
3.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88 | 2.88
3.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32 | 0.32
4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64 | 0.64
4.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56 | 2.56
4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84 | 3.84
4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92 | 1.92
4.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.56 | 5.12 | 5.12 | 5.12 | 5.12 | 5.12
5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.28 | 1.28 | 1.28
5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.84 | 5.12 | 5.12 | 5.12
5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.88 | 2.88 | 2.88 | 2.88
5.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.28 | 1.28
5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.56 | 5.12 | 5.12
5.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.92 | 1.92 | 1.92 | 1.92
5.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28 | 1.28
5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.64 | 1.28
5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28
5.10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28
5.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.28
Formulas:
Week End = [Week Start]+4